Continental Europe Support Unit: third progress report

1. Purpose of Paper

This is the third progress report to the Cochrane Collaboration Steering Group on the Continental Europe Support Unit (CESU) for Diagnostic Test Accuracy Studies, as required under Section 3.3.1 of the contract between The Dutch Cochrane Centre and The Cochrane Collaboration.

2. Urgency

Low (information only).

3. Access

Open.

4. Background

The aim of this project is to assist Cochrane Review Groups (CRGs) and Cochrane Centres, located in Continental Europe, with the implementation of methods and procedures for developing Cochrane Reviews of Diagnostic Test Accuracy (DTA). The Continental Europe Support Unit (CESU) collaborates closely with the UK Support Unit (UKSU), located in Birmingham. For more information: http://srdta.cochrane.org/en/index.html

5. Discussion

Progress is reported according to the Deliverables and Outputs, mentioned in the contract.

Deliverables and Outputs

CRG Support

- To work with the Continental European CRG bases as and when they are able, to bring them on line with reviews of test accuracy, helping them create topic lists and potential titles for reviews, and providing education to editorial staff in review processes for test accuracy reviews

Deliverables and timelines:

  - A document with a description of the required CRG processes / procedures with respect to test accuracy reviews

Expected delivery date: April 2008

Completed (see previous progress reports).

- To support Continental European CRGs with question formulation, search strategies, assessment of study quality and statistical analyses, and with use of the RevMan software

Deliverables and timelines:

  - Help desk for CRGs, Cochrane methodologists and Cochrane Centres, based in Continental Europe: second line consultancy for requests for assistance with question formulation, search strategies, assessment of study quality and statistical analyses, and with use of the RevMan software

Expected delivery date: throughout 2007 and 2008

Consultation re DTA issues has been delivered on an ad hoc basis.

Induction training of continental CRGs has been planned. In October, we will visit the CRGs in Copenhagen to provide induction training of those CRGs on the spot. We will further assist those trained CRGs with the implementation of their first DTA reviews.

One of the CESU members (backed up by Cochrane TSCs and members of the Information Retrieval Methods Group) participates in explorative discussions with Elsevier about adequate tagging of DTA studies in Embase.

  - Intensive support with the first Continental European CRGs’ 1-2 diagnostic reviews

Expected delivery date: throughout 2007 and 2008

See also previous progress reports and item 2.1: trained CRGs will be intensively supported with the execution of their first DTA reviews.

- To organise methodological peer review of protocols and reviews of test accuracy

Deliverables and timelines:

  - Formation of a network of methodological peer reviewers

Expected delivery date: December 2007

Completed (in collaboration with UKSU). Candidate members of the DTA Editorial Team will be proposed to the CCSG for approval.

  - Checklist for methodological and statistical peer review of Cochrane reviews of test accuracy

Expected delivery date: March 2008

A draft checklist has been developed and is currently being piloted on the pilot reviews. We expect to finalise the checklist in October 2008.

  - Methodological peer review of 5 (2007) / 10 (2008) protocols and reviews of test accuracy

Expected delivery date: throughout 2007 and 2008

See also previous progress reports.

We have started with peer-review of a DTA protocol that was already published in The Cochrane Library and expect to receive an increasing number of protocols and finalised versions of the pilot reviews in the coming months.

Training

- Development of training courses for (a) CRG editorial teams, (b) review authors and (c) Centre staff

Deliverables and timelines:

  - Workshop (including syllabus) for CRG editorial teams and Cochrane Centre staff.

Expected delivery date: April 2007

Completed (see previous progress reports). We will update the course materials regularly.

  - Workshop (including syllabus) for Review Authors.

Expected delivery date: August 2007

In collaboration with UKSU an author workshop has been developed (see also item 6.2). We will update the course materials regularly.

- Contribute to the development of an advanced training course for (Cochrane) methodologists in systematic reviews of diagnostic test accuracy

Deliverables and timelines:

  - To develop, in close collaboration with UKSU, an international training course for methodologists in systematic reviews of diagnostic test accuracy.

Expected delivery date: December 2007

This workshop has been postponed to June 2009. Members of CESU will assist with the development of course materials (see also item 7.1).

- To run a regular programme of training courses for CRG editorial teams, Centre staff and review authors in the region

Deliverables and timelines:

  - Two workshops for Cochrane Editors, other CRG staff and Centre staff during the annual Continental European Cochrane Entities Meeting

Expected delivery dates: May 2007 and May 2008

See also previous progress reports.

In May 2008, we have updated the participants of the Continental European Cochrane Entities Meeting in Milan, Italy, on current developments re DTA reviews.

On October 2, 2008, we will run a workshop for editorial teams and Centre staff involved with training in Freiburg, just before the start of the Cochrane Colloquium (pre-Colloquium workshop). Members from Cochrane entities that currently aren’t supported by a support unit are strongly encouraged to attend.

  - Two workshops for review authors (in close collaboration with a Cochrane Centre) in 2007 and 2008

Expected delivery dates: September 2007 and September 2008

In collaboration with UKSU we ran the first author workshop from 19-20 June 2008 in Amsterdam. There were 20 participants: 10 from continental Europe, seven from the UK, two from the USA and one from Israel.

- To run, in close collaboration with UKSU, an international training course for methodologists in systematic reviews of diagnostic test accuracy

Deliverables and timelines:

  - Participation in an international course for methodologists

Expected delivery date: September 2008

This workshop will be organised by UKSU in June 2009 in Birmingham. Members of CESU will assist.

Tools

- Creation of an instruction manual and tutorials for the new Diagnostic Accuracy RevMan software

Deliverables and timelines:

  - Beta-testing of RevMan 5 – Report of the evaluations

Expected delivery date: January 2007 (conditional on RevMan 5 availability)

Completed (see previous progress reports).

  - Contribution to the instruction manual for the new Diagnostic Accuracy RevMan software (RevMan User Guide)

Expected delivery date: August 2007 (conditional on RevMan 5 availability)

Completed (see previous progress reports).

  - Tutorial for the new Diagnostic Accuracy RevMan software (similar to current RevMan 4.2 exercise)

Expected delivery date: August 2007 (conditional on RevMan 5 availability)

We will run a workshop “RevMan 5 for Cochrane Diagnostic test accuracy reviews” for staff at Cochrane Centres and Review Group Coordinators at the Freiburg Colloquium. During this workshop the RevMan DTA tutorial (formerly called “RevMan exercise”) will be demonstrated.

- To contribute to the Diagnostic Accuracy Reviewers’ Handbook

Deliverables and timelines:

  - Detailed review of the draft Handbook, including corrections and proposed amendments

Expected delivery date: January 2007

Members of UKSU and CESU have extensively contributed to the handbook, not only by reviewing the various chapters, but also by writing major sections. This work is ongoing.

Development

- To work with the Collaboration publishers in the design and testing of publication software

Deliverables and timelines:

  - Piloting and testing the software – Report of the evaluations

Expected delivery date: depends on the software availability

This work is still in progress (see also previous progress reports).

Rob Scholten

Dutch Cochrane Centre / CESU

28/8/2008