Register of Reports of Diagnostic Test Accuracy: second progress report

1. Purpose of Paper

This is the second progress report to the Cochrane Collaboration Steering Group on the Register of Reports of Diagnostic Test Accuracy Studies, as required under Section 3.3 of the contract between the Cochrane Renal Group and The Cochrane Collaboration.

2. Urgency

Not urgent – information only.

3. Access

Open.

4. Background

The Cochrane Renal Group, in consultation with the Cochrane Reviews of Diagnostic Test Accuracy Working Group (CRDTA), developed a proposed model for the register. This was circulated for comment to all Cochrane entities during March/April 2006. The original proposal can be viewed at http://www.cochrane.org/docs/diagnosticproposal.htm .

The Cochrane Renal Group’s proposal for funding to manage the development of the register was part of the broader application for funding to support systematic reviews of diagnostic test accuracy submitted to the CCSG in April 2006. The CCSG approved two-year funding for the register.

A two-year plan was then developed (see http://www.cochrane.org/docs/DiagnosticTestRegisterPlan.doc), and the contract, based on the plan, was signed on October 24th 2006 at the Cochrane Colloquium in Dublin.

5. Discussion

Progress (bullet points, in italics) is reported based on the Deliverables and Outputs under Schedule 1 of the Project Plan in the contract, as listed below. Progress made since the Firstt Progress Report is highlighted in Bold italics).

- Deliverables and Outputs

  - Year 1

    - Education and Training

- Development of a training package for TSCs in conjunction with the Regional

Support Unit in the Netherlands and the School of Public Health, University of Sydney.

- Literature search on online training carried out.

- Contact Australasian Cochrane Centre and IMS staff responsible for developing and formatting the Open Learning materials.

- ACC staff contacted.

2.1.2  Development of Register Framework

a)	Development of register framework (database software, structure, 	processes, etc.).

- Reference Manager (v.11) is being used as the initial software to hold records for screening, coding etc. Reference Manager databases have been set up, fields modified, filters tested, Procedures Manual begun.

- The additional fields are: Index Test, Reference Standard, Target Condition, Population, Source Database, Related SR (for records sourced from existing systematic reviews).

- Procedures Manual further developed to ensure consistency and quality of register.

b) Search strategy reference group formed, e.g. Mariska Leeflang, Julie

Glanville and other experts in the field of search strategy development.

- Mariska Leeflang, Julie Glanville and Marie Westwood contacted September 2006. First meeting held 24th October 2006 during Cochrane Colloquium. All three have agreed to form reference group for the Register, to provide comment and advice on search strategies and protocols as developed by Ruth Mitchell

- Search strategy protocols developed.

Two main approaches have been taken:

- One is to find primary studies in already existing systematic reviews of diagnostic tests accuracy studies (DTAS).

  - A MEDLINE search for systematic reviews of DTAS has been completed and records downloaded into Reference Manager and screened. Similarly the DARE and HTA databases on the Cochrane Library have been searched and records downloaded and screened. From a total of 1527 records, 939 have been retained. Full text is being obtained, and studies from the reviews are being downloaded from MEDLINE.

    - 657 records of DTAS from 20 systematic reviews have been downloaded into the Register and coded

  - Authors of pilot Cochrane reviews will be contacted and asked to forward relevant studies from their reviews.

    - 5 have responded, and records have been included in Register

  - Julie Glanville and Marie Westwood have offered records of studies sourced for reviews they have worked on.

  - Mariska Leeflang has sent records of studies from reviews used in her work testing existing search strategies for locating DTAS in MEDLINE.

    - These are currently being formatted for inclusion.

  - The Medion database (free) will be searched for other systematic reviews not found via MEDLINE or the pilot review.

  - The InfoPOEMS database will also be searched – Wiley now own this database, and the principle author of the diagnostic test component is a member of the Primary Health Care Field, so hopefully collaboration will be easy.

- The second approach is to develop a specific search strategy for MEDLINE using methodological terms that will yield a “do-able” number of records to screen, and so enable the register to be quickly populated with records covering a wide range of topics. A variety of search strategies have been tested, and the results discussed with the Reference Group. Work continues on this approach.

- A third approach has been to include references from the Renal Group’s register of DTAS. 520 records have been included in the register.

- Screening protocols developed.

- A test database of 915 possible DTAS records downloaded from MEDLINE has been screened by RM and all members of the reference group. A teleconference is being held on 21st September to discuss areas of uncertainty (each record was screened by 3 people; records coded as “Yes” by only one person, or “Maybe” by 2 or 3 people will be discussed). Results of the screening process will be presented as part of RM’s oral presentation on development of the register at the XV Cochrane Colloquium in October 2007. Remaining areas of uncertainty will be referred to the CRDTA Working Group for discussion and resolution.

- Coding protocols developed.

- This relates to the content of fields such as Index Test, Reference Standard, Target Condition.

- An Excel database of Index Test, Reference Test, Target Condition and Population/Setting terms used in the abstracts of records downloaded into the Register has been set up. There are currently 109 Index Test, 70 Reference Test, 20 Target Condition and 23 Population/Setting terms entered. There are many synonyms – discussion with wider Cochrane diagnostic test community will be needed to standardise.

- Database tested using diagnostic test accuracy reports sourced from pilot Cochrane reviews and non-Cochrane reviews.

- A screen-shot of the register is included at the end of this report

- There are currently 1207 records in the Register

- Discussion initiated with IMS team to ensure DTAS register is included in IMS software developments and is compatible with redeveloped CENTRAL.

- Brief email contact with Monica Kjeldstrøm when initial proposal circulated IN March 2006.

2.1.3	Support for pilot review authors and TSCs regarding individual reviews

a)	Contact authors of pilot reviews for details of DTAS already found.

- Authors contacted 14th May 2007 with offer of support.

b)	Provide comments on search strategies of individual pilot reviews if requested to do so.

- No requests received as yet. Most pilot reviews are probably beyond this stage. Will remind authors of this when contacting them regarding 2.1.3.a) above.

Ruth Mitchell

Cochrane Renal Group

18/09/2007